## Sheet1
Task Name | Start | End | Duration (days) | Person Assigned
Project Deliverable 0 | 2018-02-07 | 2018-02-11 | 4 | Team
Project Deliverable 1 | 2018-02-12 | 2018-02-25 | 13 | Team
Develop prototypes | 2018-02-26 | 2018-03-04 | 6 | Team
Project Deliverable 2 | 2018-02-26 | 2018-03-11 | 13 | Team
Vet HAPI server options and backup options and choose a technology. | 2018-03-05 | 2018-03-12 | 7 | Marcos/Rafay
Complete docker integration with prototype and test running on different system | 2018-03-12 | 2018-03-19 | 7 | Cheryl
Project Deliverable 3 | 2018-03-12 | 2018-04-01 | 20 | Team
Develop educational materials for loading into database. | 2018-03-20 | 2018-03-27 | 7 | Jennifer
Develop framework (a base template) for developing the curriculum elements based on one of the liver diseases | 2018-03-20 | 2018-03-27 | 7 | Team
Develop Docker infrastructure for creating containers. | 2018-03-20 | 2018-03-27 | 7 | Cheryl
Develop code for sequencing container start up. | 2018-03-28 | 2018-04-05 | 8 | Cheryl
Develop working application framework for one disease | 2018-03-28 | 2018-04-05 | 8 | Team
Develop front end web page. | 2018-03-28 | 2018-04-05 | 8 | Andy/Marcos/Rafay
Develop threejs and 3D model integration with web page. | 2018-03-28 | 2018-04-05 | 8 | Andy
Develop patient data FHIR json files for patients. | 2018-03-28 | 2018-04-04 | 7 | Rafay
Develop MySQL database schema | 2018-03-28 | 2018-03-30 | 2 | Jennifer
Develop MySDQL datbase loading automation. | 2018-03-28 | 2018-04-05 | 8 | Jennifer/Cheryl
Find or develop textures for the organ 3D visualizations. | 2018-03-28 | 2018-04-05 | 8 | Team
Develop solution to issue with 3D models maintaining correct colors. | 2018-03-28 | 2018-04-05 | 8 | Andy
Develop Java connector to read FHIR data and write to db. | 2018-03-28 | 2018-04-04 | 7 | Marcos
Develop FHIR server data loading automation. | 2018-03-28 | 2018-04-04 | 7 | Cheryl
Develop flask, web page and db integration. | 2018-03-28 | 2018-04-05 | 8 | Jennifer/Cheryl
Project Deliverable 4 | 2018-04-02 | 2018-04-22 | 20 | Team
Project Deliverable 5 | 2018-04-02 | 2018-04-22 | 20 | Team
Normalize all of the models to be consistent | 2018-04-05 | 2018-04-12 | 7 | Andy
Complete interactive tutorials for 3-5 diseases. | 2018-04-13 | 2018-04-20 | 7 | Team
Complete user acceptace testing. | 2018-04-21 | 2018-04-22 | 1 | Team
Complete presentations(s). | 2018-04-21 | 2018-04-22 | 1 | Team